## Tabelle1
Step | TypeReference | Chapter | Workflow | Status | Remarks
| Chapter | 1 | Set-up | Done
|  |  | CreateWorkspace | Done |  | Not started
0001 | User Guide | UG4.2.02 | CreateProject | Done | Revisit for folder structure | In Progress
0002 | Confluence | Confluence01_SwcApplConfiguration_01 | CreateNewProjectFromScratch | Done | Revisit for folder structure | Blocked
| Chapter | 2 | Configuration - SwcAppl | Done |  | Done
0003 | User Guide | UG4.2.03 | CreateApplicationDataType | Done |  | Done
0004 | Confluence | Confluence01_SwcApplConfiguration_02 | CreateApplicationDataType | Done
0005 | User Guide | UG4.2.04 | CreateDataTypeMappingSet | Done
0006 | Confluence | Confluence01_SwcApplConfiguration_03 | CreateNewDataTypeMappingSet | Done
0007 | User Guide | UG4.2.05 | CreateSenderReceiverPortInterface | Done
0008 | Confluence | Confluence01_SwcApplConfiguration_04 | CreateNewSenderReceiverPortInterface | Done
0009 | User Guide | UG4.2.06 | CreateApplicationSWComponentType | Done
0010 | Confluence | Confluence01_SwcApplConfiguration_05 | CreateNewSWCPrototypes | Done
0011 | User Guide | UG4.2.07 | CreatePorts | Done
0012 | Confluence | Confluence01_SwcApplConfiguration_06 | CreateNewPorts | Done
0013 | User Guide | UG4.2.08 | CreateInternalBehaviorContainer | Done
0014 | Confluence | Confluence01_SwcApplConfiguration_07 | CreateNewInternalBehaviorContainers | Done
0015 | User Guide | UG4.2.09 | CreateRunnableEntity | Done
0016 | Confluence | Confluence01_SwcApplConfiguration_08 | CreateNewRunnables | Done
0017 | User Guide | UG4.2.10 | CreateDataAccessPoints | Done
0018 | Confluence | Confluence01_SwcApplConfiguration_09 | CreateNewDataAccessPoints | Done
0019 | User Guide | UG4.2.11 | CreateTimingEvents | Done
0020 | Confluence | Confluence01_SwcApplConfiguration_10 | CreateNewTimingEvents | Done
0021 | User Guide | UG4.2.12 | InstantiateSWCsintoComposition | Done
0022 | Confluence | Confluence01_SwcApplConfiguration_11 | InstantiateSWCsintoComposition | Done
0023 | User Guide | UG4.2.13 | CreateConnections | Done
0024 | Confluence | Confluence01_SwcApplConfiguration_12 | CreateManualConnections | Done
| Chapter | 3 | Configuration - System | In Progress
0025 | User Guide | UG4.3.02 | ImportDBC | Done | Use latest real project DBC
0026 | Confluence | Confluence02_SystemConfiguration_01 | ImportNewDBC | Done | Use latest real project DBC
0027 | User Guide | UG4.3.03 | CreateSystemDescription | Done
0028 | Confluence | Confluence02_SystemConfiguration_02_CreateSystemDescription_01 | CreateNewSystem | Done
0029 | Confluence | Confluence02_SystemConfiguration_02_CreateSystemDescription_02 | SetCategoryToSYSTEM_DESCRIPTION | Done
0030 | Confluence | Confluence02_SystemConfiguration_02_CreateSystemDescription_03 | ConfigureReferenceToComposition | Done
0031 | User Guide | UG4.3.04 | MapSWCsToApplicationECU | Done
0032 | Confluence | Confluence02_SystemConfiguration_02_CreateSystemDescription_04 | MapSWCsToEcuInstance | Done
0033 | User Guide | UG4.3.05 | SystemDataMapping | In Progress | Revisit on need basis
0034 | Confluence | Confluence02_SystemConfiguration_02_CreateSystemDescription_05 | MapSystemData | In Progress | Revisit on need basis
| Chapter | 4 | Configuration - ECU
0035 | User Guide | UG4.4.02 | CreateECUExtract | Not started
0036 | Confluence | Confluence03_EcuConfiguration_01 | CreateEcuExtract | Not started
0037 | User Guide | UG4.4.03 | GenerateECUC | Not started
0038 | Confluence | Confluence03_EcuConfiguration_02 | ConfigureEcuCValueCollection | Not started
0039 | User Guide | UG4.4.04 | CreateConfigureCompiler | Not started
0040 | User Guide | UG4.4.05 | CreateConfigurePlatform | Not started
0041 | User Guide | UG4.4.06 | CreateConfigureBfx | Not started
0042 | User Guide | UG4.4.07 | CreateDet | Not started
0043 | Confluence | Confluence03_EcuConfiguration_05_ConfigureAndGenerateBsw_01 | Configure | Not started
0044 | Confluence | Confluence03_EcuConfiguration_05_ConfigureAndGenerateBsw_02 | IntegrateConfigurationsFromStarterKit | Not started
0045 | Confluence | Confluence03_EcuConfiguration_05_ConfigureAndGenerateBsw_03 | GenerateCode | Not started
0046 | Confluence | Confluence03_EcuConfiguration_06 | MapBswServiceSWCsOntoComposition | Not started
0047 | Confluence | Confluence03_EcuConfiguration_07_01 | GenerateCodeRTE | Not started
0048 | Confluence | Confluence03_EcuConfiguration_07_02 | GenerateCodeOS_FAILED | Not started
0049 | Confluence | Confluence03_EcuConfiguration_07_02 | GenerateCodeOS_PASSED | Not started
0050 | Confluence | Confluence03_EcuConfiguration_07_03 | ReGenerateBSW | Not started
| Chapter | 5 | Configuration - Memory Stack
0051 | Confluence | Confluence04_MemoryStackConfiguration_04_01 | PimCreationInAswConfiguration | Not started
0052 | Confluence | Confluence04_MemoryStackConfiguration_04_02 | CreateNvMServiceNeeds | Not started
0053 | Confluence | Confluence04_MemoryStackConfiguration_04_04 | ConfigurationGeneration | Not started
0054 | Confluence | Confluence04_MemoryStackConfiguration_04_05 | BswCodeGeneration_PASSED | Not started
0055 | Confluence | Confluence04_MemoryStackConfiguration_04_06 | AddNvMServiceComponentToComposition | Not started
0056 | Confluence | Confluence04_MemoryStackConfiguration_04_07 | CreateConnectionBetweenReceiverSwcAndNvMServiceComponent | Not started
0057 | Confluence | Confluence04_MemoryStackConfiguration_04_08 | UpdateEcuExtract_FAILED | Not started
0058 | Confluence | Confluence04_MemoryStackConfiguration_04_09 | MapSwcServiceRunnablesToOsTaskBsw | Not started
0059 | Confluence | Confluence04_MemoryStackConfiguration_04_10 | RteGeneration | Not started
0060 | Confluence | Confluence04_MemoryStackConfiguration_04_11 | McalUpdate | Not started
0061 | Confluence | Confluence04_MemoryStackConfiguration_04_12 | AswUpdate | Not started
| Chapter | 6 | Configuration - Mode Management
0062 | User Guide | UG4.5.02 | CreateEcuM | Not started
0063 | User Guide | UG4.5.02.1 | EcuMCommonConfiguration | Not started
0064 | User Guide | UG4.5.02.2 | EcuMDriverInitItems | Not started
0065 | User Guide | UG4.5.02.3 | EcuMWakeupSources | Not started
0066 | User Guide | UG4.5.02.4 | EcuMFlexConfiguration | Not started
0067 | User Guide | UG4.5.03 | ModeManagementDataTypes | Not started
0068 | User Guide | UG4.5.04.1 | ConfigureBswMGeneral | Not started
0069 | User Guide | UG4.5.04.2 | ConfigureBswMUserIncludeFiles | Not started
0070 | User Guide | UG4.5.04.3 | ConfigureBswMDataTypeMappingSets | Not started
0071 | User Guide | UG4.5.04.4 | ConfigureBswMModeRequestPort | Not started
0072 | User Guide | UG4.5.04.5 | ConfigureBswMModeConditions | Not started
0073 | User Guide | UG4.5.04.6 | ConfigureBswMLogicalExpressions | Not started
0074 | User Guide | UG4.5.04.7 | ConfigureBswMActions | Not started
0075 | User Guide | UG4.5.04.8 | ConfigureBswMActionLists | Not started
0076 | User Guide | UG4.5.04.9 | ConfigureBswMRules | Not started
| Chapter | 7 | Configuration - Os & RTE
0077 | User Guide | UG4.6.02 | ImportFromExampleFolder | Not started
0078 | User Guide | UG4.6.03 | ConfigureEcucValueCollection | Not started
0079 | User Guide | UG4.6.04 | GenerateSWCDandBSWMD | Not started
0080 | User Guide | UG4.6.05 | MapBswModulesToComposition | Not started
0081 | User Guide | UG4.6.06.1 | ConfigureOsGeneralSettings | Not started
0082 | User Guide | UG4.6.06.2 | ConfigureInitTask | Not started
0083 | User Guide | UG4.6.06.3 | ConfigureOsTask_ASW | Not started
0084 | User Guide | UG4.6.06.4 | ConfigureOsTask_BSW | Not started
0085 | Confluence | Confluence03_EcuConfiguration_03_ConfigureOs_01 | CreateOsTask | Not started
0086 | User Guide | UG4.6.07 | MapRunnablesToOsTasks | Not started
0087 | Confluence | Confluence03_EcuConfiguration_04_ConfigureRte_02 | MapRunnablesToOsTask | Not started
0088 | User Guide | UG4.6.08 | CreateAdditionalBswModuleInstances | Not started
0089 | User Guide | UG4.6.09 | CreateBswMModeGroupConnection | Not started
0090 | User Guide | UG4.6.10 | RteCodeGeneration | Not started
0091 | User Guide | UG4.6.11 | Post-RteOsConfiguration | Not started
0092 | User Guide | UG4.6.12 | OsGeneration-FAILED | Not started
0093 | User Guide | UG4.6.12 | OsGeneration-FAILED_after_Namb_support | Not started
0094 | User Guide | UG4.6.06.1 | ConfigureOsGeneralSettings | Not started
0095 | User Guide | UG4.6.06.2 | ConfigureInitTask | Not started
0096 | User Guide | UG4.6.06.3 | ConfigureOsTask_ASW | Not started
0097 | User Guide | UG4.6.06.4 | ConfigureOsTask_BSW | Not started
0098 | User Guide | UG4.6.07 | MapRunnablesToOsTasks | Not started
0099 | User Guide | UG4.6.08 | CreateAdditionalBswModuleInstances | Not started
0100 | User Guide | UG4.6.09 | CreateBswMModeGroupConnection | Not started
| Chapter | 8 | Code generation
0101 | User Guide | UG4.6.10 | RteCodeGeneration | Not started
0102 | User Guide | UG4.6.11 | Post-RteOsConfiguration | Not started
0103 | User Guide | UG4.6.12 | OsGeneration-FAILED | Not started
0104 | User Guide | UG4.6.12 | OsGeneration-PASSED | Not started | Refer back again: OS generation for Real ECU
0105 | User Guide | UG4.6.13 | MemMapGeneration | Not started
0106 | User Guide | UG4.6.14 | McALGeneration | Not started | Refer confluence "How to Create a Cdd SWC to access MCAL Module"
| Chapter | 9 | Integration and Building
0107 | User Guide | UG4.7.02 | IntegrateMcALandBSW | Not started
0108 | User Guide | UG4.7.03 | BuildProjectExecutable | Not started
0109 | Confluence | Confluence06_E2EConfiguration_4.3.1 | CreateSenderReceiverInterface | Not started
0110 | Confluence | Confluence06_E2EConfiguration_4.3.2 | E2EDataInterfaceConfiguration | Not started
0111 | Confluence | Confluence06_E2EConfiguration_4.3.3 | CreateAndConfigureE2ESWC | Not started
0112 | Confluence | Confluence06_E2EConfiguration_4.3.4 | CreateDataAccessPointsForE2ESWC | Not started
0113 | Confluence | Confluence06_E2EConfiguration_4.3.5 | CreateDataReceiveEvent | Not started
0114 | Confluence | Confluence06_E2EConfiguration_4.3.6 | ConnectE2ESWC | Not started
0115 | Confluence | Confluence06_E2EConfiguration_4.3.7 | CreateE2EModule | Not started
0116 | Confluence | Confluence06_E2EConfiguration_4.3.8 | CreateCrcModule | Not started
0117 | Confluence | Confluence06_E2EConfiguration_4.3.9 | BswCodeGeneration | Not started
0118 | Confluence | Confluence06_E2EConfiguration_4.3.10 | Mapping The Event | Not started
0119 | Confluence | Confluence06_E2EConfiguration_4.3.11 | RTA-RTE Code Generation | Not started
0120 | Confluence | Confluence06_E2EConfiguration_4.3.12 | E2E Protection Wrapper (E2EPW)/ Application Software | Not started
| Chapter | 10 | Virtual ECU
0121 |  |  | vEcu - CMakeBuild - cygwin | Not started
| Chapter | 11 | Real ECU
0122 | Confluence |  | How to configure DCM UDS with the DEXT Editor | Not started | More details to follow later.