## Tabelle1
Sl No. | Priority | Ideal time for introduction | Return on Investment | Impact | Complexity | Scope | Activity | Description | Remarks
1 | 1 | Before first in-vehicle testing | High | Mid | Mid | McAL, Com stack, RTE, Application | CANFD/Flexray/Eth broadcasting of application inputs
2 | 1 | Before first in-vehicle testing | High | Mid | High | Com McAL drivers | .asc log based simulation replay on PC
3 | 1 | Before first in-vehicle testing | High | Mid | High | Com McAL drivers | Log parsing - Com stack optimization for simulation on PC
4 | 1 | Before first in-vehicle testing | High | Mid | High | Com McAL drivers | Log regeneration during ReSim execution on PC
5 | 1 | Before first in-vehicle testing | High | Mid | High | RTE - Appllication interfaces | c# based SIL on CANoe |  | Extend c function calls from c# interface functions - simple implementation
6 | 1 | Before first in-vehicle testing | High | Mid | Low | Crypto stack, Com stack | Cyber-security / Crypto stack simulation on PC
7 | 1 | Before first in-vehicle testing | High | Mid | Low | AUTOSAR configuration, NVM | AUTOSAR configurations as NV blocks
8 | 1 | Before first in-vehicle testing | High | Mid | Low | AUTOSAR configuration, NVM | Default generated AUTOSAR configurations
9 | 1 | Before first in-vehicle testing | High | Mid | High | Dcm, NVM | Downloadable AUTOSAR configurations
10 | 1 | Before first in-vehicle testing | High | Mid | High | RTOS, SchM, Com stack | Timing optimization/accuracy of communication on bus
11 | 1 | Before first in-vehicle testing | High | Mid | High | McAL | McAL simulation on PC
12 | 1 | Before first in-vehicle testing | High | Mid | High | McAL | uC porting
13 | 1 | Before first in-vehicle testing | High | Mid | Mid | EcuAb | ECU porting
14 | 1 | Before first in-vehicle testing | Mid | High | High | Dcm, other connected modules/Application | cmd prompt based Diagnostic execution |  | Dem, Dcm, <Det>, <FiM> simulation on PC
15 | 2 | Before first software delivery | High | High | Low | Build toolchain | Make --> cmake
16 | 2 | Before first software delivery | High | High | HIgh | Build toolchain | Parallel cmake for PC and cross-compilation
17 | 2 | Before first software delivery | High | High | High | Build toolchain | cmake based linker/loader file |  | At least initial version, it can be continuous development later
18 | 2 | Before first software delivery | High | Mid | Low | RTE, Com service modules, Application | RTE global buffer for (uplink/downlink) signals
19 | 2 | Before first software delivery | High | Mid | High | McAL, Com stack, RTOS, SchM, RTE, Application | Timing/resolution/correctness accuracy of logging application outputs
20 | 2 | Before first software delivery | Mid | High | Mid | Complete software | Debug on Virtual target with simulated McAL |  | Entire Software except McAL, <AUTOSAR generated?>
21 | 2 | Before first software delivery | Mid | High | HIgh | Common | Compiler configuration/porting
22 | 2 | Before first software delivery | Mid | Mid | Mid | McAL | McAL library set-up
23 | 2 | Before first software delivery | Mid | Mid | Mid | EcuAb | EcuAb library set-up
24 | 2 | Before first software delivery | Mid | Mid | Low | Application | Application porting
25 | 2 | Before first software delivery | Low | Mid | Mid | Application | Application library
26 | 3 | Early in the project start | High | Mid | Mid | McAL | Device driver specific uC header break-down
27 | 3 | Early in the project start | Mid | High | Low | Complete software, except generated code | .h --> .hpp
28 | 4 | Continuous development process | High | High | Low | Complete software, except generated code | .cpp/.hpp source file templates
29 | 4 | Continuous development process | Mid | High | Low | Complete software, except generated code | Consolidate consts on Flash
30 | 4 | Continuous development process | Mid | High | Low | Complete software, except generated code | Consolidate contexts on RAM/stack
31 | 4 | Continuous development process | Mid | High | Low | Complete software, except generated code | One-on-One module interface headers
32 | 4 | Continuous development process | Mid | High | High | Complete software, except generated code | .c --> .cpp
33 | 4 | Continuous development process | Mid | Mid | Low | Application | AUTOSAR runnables (Application optimization)
34 | 4 | Continuous development process | Mid | Mid | Low | Service layer | AUTOSAR runnables (Services optimization)
35 | 4 | Continuous development process | Mid | Mid | Low | EcuAb | AUTOSAR runnables (EcuAb optimization)
36 | 4 | Continuous development process | Mid | Mid | Low | McAL | AUTOSAR initializations (McAL optimization)
37 | 4 | Continuous development process | Mid | Mid | Mid | All state machine modules | System level modules to have state machine contexts + optimizations
38 | 4 | Continuous development process | Mid | Mid | High | RTOS Task schedule configurations | RTOS timing optimization
39 | 4 | Continuous development process | Low | High | Mid | Application | Execution of entire application on unit testing environment
40 | 4 | Continuous development process | Low | High | High | AUTOSAR stack | Execution of entire AUTOSAR stack on unit testing environment |  | Only for hand coded modules
41 | 4 | Continuous development process | Low | Mid | High | Com stack | Communication stack buffer optimization
42 | 4 | Continuous development process | Low | Mid | High | Application | Application execution optimization
43 | 5 | Before vehicle production | High | High | High | Bootloader, Dcm, Fls | FOTA
44 | 5 | Before vehicle production | High | HIgh | High | Bootloader | Bootloader to re-use AUTOSAR stack
45 | 5 | Before vehicle production | High | Mid | High | Bootloader | "Move" device drivers to bootloader
46 | 5 | Before vehicle production | High | High | High | AUTOSAR stack | Downloadable Adaptive AUTOSAR modules
47 | 6 | Early in new HW change programs | High | High | High | HW | Daughter board: uC |  | Involvement with Hardware R&D responsible and create development boards for R&D engineers (HW, SW, Sys, Testing etc)?
48 | 6 | Early in new HW change programs | High | High | High | HW | Daughter board: Communication chip-set circuitry |  | Involvement with Hardware R&D responsible and create development boards for R&D engineers (HW, SW, Sys, Testing etc)?
49 | 6 | Early in new HW change programs | Mid | High | High | HW | Daughter board: Power supply circuitry |  | Involvement with Hardware R&D responsible and create development boards for R&D engineers (HW, SW, Sys, Testing etc)?
50 | 6 | Early in new HW change programs | Low | High | High | HW | Daughter board: EcuAb - Application specific |  | Involvement with Hardware R&D responsible and create development boards for R&D engineers (HW, SW, Sys, Testing etc)?